## Sheet1
Learning goal 1 |  |  |  | Learning goal 2
Date | Time | Hours | Activity | Date | Time | Hours | Activity
2022-03-20 | 17.00 - 18.30 | 1.5 | Working on scene layout | 2022-05-25 | 14.45 - 15.30 | 0.75 | Object pooling
2022-03-21 | 15.00 - 18.00 | 3 | Setting up VR | 2022-06-10 | 12.00 - 13.30 | 1.5 | Started writing optimization research doc. Tried upgrading to HDRP (didn't work, asset pack incompatible)
2022-03-22 | 13.00 - 15.00 | 2 | Random enemy spawning, player canvas, shop canvas | 2022-06-13 | 12.45 - 15.00 | 2.25 | Lighting, research doc
2022-03-29 | 9.15 - 16.00 | 6.75 | Fixed controller behaviour. NPC model add, gun functionality
2022-03-31 | 10.30 - 12.00 | 1.5 | Fixed enemy animations
2022-04-04 | 10.15 - 12.30 | 2.25 | Worked on gun system
2022-04-04 | 13.30 - 17.00 | 3.5 | Worked on gun system
2022-04-08 | 20.00 - 21.00 | 1 | Worked on enemy FSM
2022-04-09 | 10.00 - 12.00 | 2 | Worked on enemy FSM
2022-04-11 | 9.30 - 15.00 | 5.5 | Enemy FSM, sound
2022-04-12 | 9.00 - 14.00 | 5 | Level design
2022-04-13 | 9.00 - 14.00 | 5 | Level design
2022-04-14 | 10.00 - 12.30 | 2.5 | Level design, background music player
2022-05-18 | 9.00 - 12.00 | 3 | Continuing for redo. Refining enemy behaviour
2022-05-19 | 14.30 - 16.30 | 2 | Working on gunplay, refining enemy AI
2022-05-20 | 8.30 - 12.00 | 3.5 | Working on a main menu
2022-05-23 | 15.00 - 16.30 | 1.5 | Worked on shop
2022-05-24 | 10.30 - 12.30 | 2 | Worked on level, shop UI functionality
2022-05-25 | 14.00 - 14.45 | 0.75 | Shop functionality
2022-05-27 | 9.45 - 12.00 | 2.25 | Level design
2022-05-30 | 10.15 - 12.30 | 2.25 | Finalized level design
2022-05-31 | 14.00 - 17.00a | 3 | Polishing gunplay
2022-06-02 | 9.00 - 11.30 | 2.5 | Fixing shop bugs
2022-06-10 | 10.30 - 12.00 | 1.5 | Polishing gunplay
|  | 65.75 |  |  |  | 4.5